# Pitch Deck 2 V2: Agri Market-Linkage & Intelligence Platform

Version objective: This V2 is an investment-grade upgrade oriented to a defined 24-month final destination.

# 1) Investment Thesis

Create a trusted transaction and data layer connecting producer groups to buyers with predictable quality and delivery.

# 2) Problem Severity & Why Now

Demand fragmentation and weak market signaling create pricing inefficiency and post-harvest losses.

# 3) Offer Architecture

Coop SaaS, buyer intelligence reports, and transaction facilitation with reliability scoring.

# 4) Go-to-Market Wedge (First 100 Customers)

Launch with concentrated crop corridors and anchor buyers to prove repeatability before geographic scale.

# 5) Partnerships Flywheel

Better data improves match quality; better matches increase GMV; rising GMV attracts more buyers and coops.

# 6) 24-Month Financial Engine (Scenario View)

| Metric | Target |
| --- | --- |
| Downside Year 2 Revenue | 56,000,000 RWF |
| Base Year 2 Revenue | 81,000,000 RWF |
| Upside Year 2 Revenue | 108,000,000 RWF |
| Target Gross Margin | 60% |
| Target EBITDA Margin (Month 24) | 28% |

# 7) Final Destination (Month 24)

FINAL DESTINATION: By Month 24, become the most trusted agri matching and transaction intelligence node in target provinces with predictable monthly GMV.

# 8) Milestone Ladder

Day 0-90: 5 coop pilots, 3 anchor buyers, first repeat transaction cycles

Month 4-12: 25 coops onboarded, reliability scoring operational, SLA performance above 90%

Month 13-24: province replication, integrated finance partnerships, strong recurring data-report revenue

# 9) KPI Command Center

Lead-to-customer conversion (%)

Monthly recurring revenue (RWF)

Gross margin (%)

CAC payback period (months)

Customer retention / churn

Contribution margin per customer

On-time payment rate (%)

Partner-sourced revenue share (%)

# 10) Risks, Kill-Criteria, and Mitigations

Risk: inconsistent supply quality. Mitigation: standardized grading and QA checkpoints.

Risk: buyer trust gap. Mitigation: contract templates and transparent performance scorecards.

Kill criterion: no repeat monthly buyer cohort by Month 9.

# 11) Final Destination Diagram (Mermaid PNG)

# 12) Source & Validation

Validation note (2026-04-18): Where live statistics were not retrievable in-session, figures are explicit planning assumptions. Verify current indicators with NISR, BNR, RURA, and RDB before investor distribution.